## Sheet1
Obtain Tech/Functional Requirements | 5 days
Clarify implant interface specifications | 3 days | 1
Identify enhancement parameters | 3 days | 1
Create Mock use cases | 6 days | 3,2
Initial Mock interface design specs | 4 days | 4
Create low-fidelity Mock prototype | 3 days | 5
Low-fidelity Mock software interface testing | 10 days | 6
Create high-fidelity Mock interface prototype | 10 days | 7
High-fidelity Mock software interface testing | 4 days | 8
Mock system analysis | 14 days | 3
Mock enhancement functional design | 10 days | 9,10
Mock add-on module functional design | 10 days | 9,10
Mock enhancement development | 30 days | 11
Mock enhancement unit testing | 3 days | 13
Mock add-on module development | 20 days | 12
Mock add-on unit testing | 2 days | 15
Create Mock-Up use cases | 3 days | 2,3
Create low-fidelity Mock-Up prototype | 5 days | 17
Low-fidelity Mock-up software interface testing | 9 days | 18
Create high-fidelity Mock-Up interface prototype | 10 days | 19
High-fidelity Mock-up software interface testing | 6 days | 20
Mock-Up software design | 10 days | 19
Mock-Up software devlopment | 20 days | 22,21
Mock-Up unit testing | 4 days | 23
Create circuit board requirements | 19 days | 2,3
Identify base OS | 10 days | 25
Configure OS constraints | 15 days | 26
Finalize initial board specifications | 20 days | 25,16,13
Order initial boards (lag) | 1 day | 28FS+20 days
Stand-alone initial board circuitry testing | 4 days | 29
Stand-alone initial board OS testing | 4 days | 29,27
Stand-alone initial board app testing | 5 days | 31,14,16
Initial board / implant communication testing | 3 days | 30
Initial board / implant security testing | 4 days | 33
Initial board / implant integration testing | 10 days | 32,34
Initial board / Mock-Up communication testing | 5 days | 30
Initial board / Mock-Up security testing | 4 days | 36
Initial board / Mock-Up integration testing | 6 days | 32,37
Finalize revision board specifications | 5 days | 35,38
Order revision boards (lag) | 1 day | 39FS+15 days
Stand-alone revision board circuitry testing | 4 days | 40
Stand-alone revision board OS testing | 4 days | 40
Stand-alone revision board app testing | 5 days | 42
Revision board / implant communication testing | 3 days | 41
Revision board / implant security testing | 4 days | 44
Revision board / implant integration testing | 10 days | 45,43
Revision board / Mock-Up communication testing | 5 days | 41
Revision board / Mock-Up security testing | 4 days | 47
Revision board / Mock-Up integration testing | 6 days | 24,48
Identify case environmental requirements | 4 days | 3
Design physical device specifications | 12 days | 50
Create RFP for case | 2 days | 51
Review case proposals | 1 day | 52
Purchase cases (lag) | 1 day | 53FS+10 days
Test case physical specifications | 5 days | 54
Test board-case compatibility | 2 days | 54
Packaging design | 10 days | 51
Packaging production | 14 days | 57
Write installation instructions | 23 days | 38,49
Order final circuit boards | 1 day | 56
Order cases | 1 day | 56,55FS+10 days
Assemble first production unit | 2 days | 60,61,46,49
Create RFP for testing group | 8 days | 4,17
Submit RFP for testing | 3 days | 63FS+10 days
Contract external testing group | 10 days | 64
Comprehensive product test | 8 days | 62,65,24
Assemble 25 units for delivery | 35 days | 60,61,66,58,59
Train sales staff | 5 days | 57
Train support staff | 8 days | 66
Final Delivery | 0 days | 68,69,67